NORTON CUCKNEY HOLBECK AND WELBECK PARISH COUNCIL 
ACTION REGISTER

| OUTSTANDING PROJECTS AND ACTIONS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Name & Objectives | Start Date | Assigned Councillors | End Date | Actions |
| Dog Fouling and Fly-Tipping Project ¦ Establish surveillance measures to aid in the deterrence of fly-tipping and dog fouling. | 08/02/2024 | Cllr. James Palmer Cllr. Nancy Wright | TBD | [1] Arrange a meeting with Bassetlaw District Council to discuss the issue of fly-tipping and dog fouling in the Parish to establish what measures can be taken. [2] Meeting to take place on Friday 9th May with Samantha Huddle at BDC. [3] Report back to PC [4] Liaise with Oliver Jones over best sites to place wildlife cameras – Email sent – waiting for a response. DW to chase |
| A60 Safety Project | 14/03/2024 | Cllr. Gemma Palmer Cllr. Matthew Evans D. Cllr. Charles Adams | TBD | [1] Establish an online traffic incident reporting form. [2] Scope the costs of purchasing and installing Speed Indicator Devices. [3] Write an article for the newsletter to inform residents of the plan. [4] Publish the new form on the Facebook page [5] Advertise the new form to the Community [6] CA to liaise with Police and Crime Commissioner re: the crossroads [7] CA to continue to liaise with Police and Crime Commissioner re: the crossroads and to liaise with GP re: the project in general. |
| Cuckney Playpark Project | 12/12/2024 | Cllr. Conor Marples | TBD | [1] Contact Playdale about the warranty on the equipment. [2] Remove zipline [3] Apply for Meden Bio-Gas grant for the playpark. [4] Meeting with Playdale Ltd. For project planning meeting. [5] Lease on Cuckney play park [6] Apply for grants for equipment [7] Order picnic bench for playpark – relating to BDC grant |
| Capital Projects Committee | 14/03/2024 | Cllr. James Palmer Cllr. Nancy Wright Cllr. Conor Marples | TBD | [1] Hold the first meeting of the Capital Project Delivery Committee [2] Meet with Welbeck Estate to discuss lease on playing field and lease on Norton and Cuckney Village Hall. [3] Write to school advising them not to allow access to the bridge from the play park [4] Arrange meeting with Welbeck and with the education authorities to set the terms of the new lease. [5] Awaiting final figure from Welbeck Estates [3] Write to school to advise them of complete closure of bridge and to liaise with Welbeck Estates regarding the future of the bridge. |
| HR Committee |  | Cllr. Kelvin Wright Cllr. Jackie Cuckson Cllr. Matthew Evans Cllr. James Palmer Cllr. Nancy Wright | 07/07/2024 | [1] Open a consultation and review the TUPE status of the Clerk’s contract [2] Create a job description and model contract for the new Clerk to the Council [3] Select candidates for the post of Clerk [4] Hold interviews for the post of Clerk [5] Appoint the new Clerk [6] Open a consultation and review the TUPE status of the Lengthsman’s contract. [7] Create a revised job description and revised contract for the Lengthsman based on the Consultation. [8] Create a risk assessment for working in Holbeck [9] Implement the new contract for the Lengthsman |
| Jubilee Community Garden – Gardening | 12/06/2024 | Cllr. David Wall Cllr. Nancy Wright | TBD | [1] Find a gardening solution for the garden in Cuckney – DW to chase [2] Get quotes from different companies |

| COMPLETED PROJECTS AND ACTIONS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Name & Objectives | Start Date | Assigned Councillors | End Date | Actions |
| Newsletter Distribution | 20/01/2024 | Cllr. Jackie Cuckson | 20/04/2024 | [1] Liaise with newsletter distributors to establish which properties are being missed [2] Create a new distribution list to capture all properties [3] Create a monthly mailing list for outlying properties if applicable |
| .Gov.Uk Digital Transfer Project | 11/01/2024 | Cllr. Matthew Evans | 31/03/2024 | [1] Confirm domain provider and website and E-Mail hosting. [2] Purchase the package from ‘Parish Online’ and confirm the new domain name and inbox names. [3] Transfer data to the new website [4] Inform councillors of new inbox usernames and passwords. [5] Inform members of the public of the new website. [6] Establish Parish Council Facebook Page [6 ] Deadline for transition to new E-Mail inboxes by 31st March 2024 |
| St Winifred’s Church Bench Replacement | 09/11/2024 | Cllr. Nancy Wright | 09/05/2024 | [1] Confirm size of the bench with the PCC [2] Order Bench [3] Bench has arrived at the church |
| Holbeck Noticeboard Replacement | 09/11/2024 | Cllr. Nancy Wright | 24/05/2024 | [1] Confirm the style and colour of the new noticeboards. [2] Confirm with Nottinghamshire County Council permission to replace the boards. [3] Order new noticeboard. [4] Noticeboards to be installed on Friday 24th May 2024. |
| D-Day Celebration Event | 11/01/2024 | Cllr. Nancy Wright | 06/06/2024 | [1] Agree time for event. [2] Hire equipment and film rights. [3] Advertise event. [4] Host screening of the film. [5] Send proceeds to the Royal British Legion [6] Make final payments and close action |